## Sheet1
Date | time spent | problem / Improvement | Important items to remember | Issues faced
10.12.2023 | 4 hrs | created project, added User module, CRUD operations for User added, Bean validation added | dependencies -Spring starter JPA Starter validation Spring Starter Web MySQL connector Lombok Model Mapper | for Bean validation messeges to be catched in client side, need to add 1. API Response 2. Global exception 3. ResourceNotFoundException
11.12.2023 | 1.30 hrs | Stop, Route Entity,DTO,Repo, created, Service started for Stop